## Sheet1
| Driver | Risk | Status
| CRE | Low | Green
| MUB | Medium | Amber
| HMCIP | High | Red
RRAA/RES
PSO2800
RES
Other (Please specify)
| Theme: | Complaints | Project/ Policy Owner: | Ian Gray, Beverley Thompson Annex C
| Summary | REAG will coordinate efforts across the Prison Service to ensure that the policy and procedures in this area deliver the recommendations set in the Mubarek report, the action areas set out by HMCIP, and the requirements in law that circumscribe our work as a public body. We will seek to radically improve the confidence in this area, specifically by conducting further research into whistleblowing and refining training on the investigation of complaints of racism. The revised Order on Race Equality (PSO2800) will prohibit the inappropriate use of prisoners in this area. Pilot sites will assess the viability of using prisoner-and-staff-led mediation as an intervention strategy to address racial complaints where agreement can be reached and it is appropriate to do so. To rebuild confidence in the system we will mandate a requirement for all investigation reports to be examined by an external member of local REATs and local members who will be recruited & trained to support this high profile area. We will do so with the aim of building public, prisoner and practitioner confidence in the system of reporting and investigating complaints and racist incidents. We will agree with national stakeholders the means by which we measure success and the targets to be reached. | [8 empty] | Work to be undertaken in: February 2008 | Work to be undertaken in: January 2008 | Work to be undertaken in: September 2007 | Work to be undertaken in: August 2007 | Work to be undertaken in: July 2007 | Work to be undertaken in: June 2007
| Driver | Key Activity | Actions | Milestones | Planned cost: Staff | Planned cost: Other | Project Delivery risk | Progress | R/A/G Status this month | R/A/G Status Last Month | Column1
1 | MUB | 1. 84 - The Prison Service, the Inspectorate and the CRE should consider whether there is a need for the investigation of complaints of racism and other serious complaints to be carried out with a strong independent element built into the process. Response: Accepted in part This will form part of the complaints and racist incidents project described in the next action. Beverley Thompson/Rob Mitchell | Develop a model for a range of levels of independent involvement in complaints and RIRF processes and include amongst tools for use by establishments in first phase roll-out of Complaints and Racist Incident project. COMPLETED | 2007-04-01 | 0.1 x D 0.1 x E | £0k | Low | Completed. Work on critical situation management to be included, along with other models of external involement (including 'Holloway model'), and existing arrangements for post-completion scrutiny of RIRFs. This has now become part of the action below. Guidance for use in establishments, as part of the improved arrangements for the handling of complaints and Racist incidents has been drafted. | Green | Green | [5 empty] | As part of the wider project to undertake a staged roll-out of improved handling arrangements for complaints and racist incidents, the guidance will be further developed with the sites. DONE VP
2 | CRE | Undertake a staged roll-out of improved arrangements for the handling of complaints and racist incidents and associated measures to build prisoner confidence in the system. Beverley Thompson/Rob Mitchell | PRODUCT 1. Tools for implementing new arrangements 2. New arrangments implemented in first tranche of prison 3. Monthly progress reports to project board 4. Evaluation of first stage roll-out 5. Impact Assessment of new arrangements 6. Strategy and plan for national coverage. BENEFIT 1. Improved prisoner confidence 2. Public demonstation of compliance with RR(A)A 2000 | 1. June 2007 2. June 2007 3. Monthly, July - December 2007 4. January 2008 5. March 2008 6. March 2008 |  | £65K | Low | New arrangements launched in four prisons in June and July. Project boards involving Area Managers met regularly to oversee the work. | Green | Green | Evaluation through prisoner survey to be conducted in four prisons during January 2008. | Project Boards to continue | Project Boards to continue. |  |  | As part of the wider project to undertake a staged roll-out of improved handling arrangements for complaints and racist incidents, the guidance will be further developed with the sites. Launch of the new arrangements to commence as follows: Week commencing 4 June at Wayland 11 June at Norwich 18 June at Full Sutton 25 June at Leeds. This will include agreeing an action plan with the Governors in each site, coaching of key staff on the new arrangements to be put in place and a random survey of prisoners using the improved questionnaire to assess current levels of confidence in the systems. DONE VP
3 | CRE | Review staff complaints, grievances and conduct investigations, with improved awareness amongst managers of the consequences of poorly managed complaint/investigations. Ian Gray/Lynne Carter | PRODUCT 1. Draft PSO 8460 Conduct & Discipline to OPG for approval. COMPLETED |  |  |  | Medium | Revised PSO 8460 published on the Intranet on 18 June 2007. The Investigations training has been agreed and is being rolled out. | Green | Amber | [5 empty] | Publication of web-based PSO on HMPS Intranet. DONE VP
4 | MUB | 69 - The Prison Service policy on whistleblowing should identify the most appropriate way for staff in an exceptional case to get confidential advice from an independent outsider and to raise their concerns outside the Prison Service. It should also ensure that the members of staff of companies who contract with the Prison Service, such as escort contractors and those responsible for running the contracted out establishments, have access to the Prison Service’s whistleblowing policy. Response: Accepted. Subject to approval by Director of Personnel and any comments from Trade Unions, the PSO will be re-issued by March 2007 to emphasise the independent role of Richard Rosser more clearly. Ian Gray/Lynne Carter | PRODUCT 1. Submit revised PSO 8605 Reporting Wrongdoing to Trade Unions for comment. 2. Submit revised PSO to Dir Personnel for approval prior to issue. COMPLETED |  |  |  | Low | The revised PSO 8605 has been agreed by the head of HR Policy and implemented on 15 August 2007. | Green | Amber | [5 empty] | We will be writing to all Unions during June, advising them that the PSO will be submitted to OPG, for their approval, in its current format. DONE VP
5 | MUB | 70 - Making a false and malicious allegation that wrongdoing has taken place should be expressly stated to be a disciplinary offence, for which dismissal from the Prison Service may be an appropriate sanction. Response: Accepted. The PSO has been amended to reflect the fact that staff who make false or malicious allegations could be subject to disciplinary action, which could result in their dismissal from HMPS. Subject to approval by Director of Personnel and any comments from Trade Unions, the PSO will be reissued in March 2007. Ian Gray | PRODUCT 1. Submit revised PSO 8605 Reporting Wrongdoing to Trade Unions for comment. 2. Submit revised PSO to Dir Personnel for approval prior to issue. COMPLETED |  |  |  | High | The revised PSO 8605 has been agreed by the head of HR Policy and issued in 15 August 2007. | Green | Green
6 | MUB | 71 - Research should be conducted on how effective the obligation to report wrongdoing - and the designation of a failure to do so as a disciplinary offence - has been. This should be done by comparing the number of instances of reported wrongdoing before and after these measures were implemented. Response: Accepted in principle (subject to the availability of funding). This proposal is to be taken forward in conjunction with the Prison Service's Professional Standards Unit. The mechanism for delivery has been considered and research will begin by April 2007, subject to the availability of additional funding. Beverley Thompson | PRODUCT 1. Undertake a scoping study 2. Commence further research | 1. February 2007 2. End October 2007 |  | likely cost of research estimated at at least £100k per year | High | Scoping study was completed in Feb 07 which concluded that the most efficient & cost effective way of carrying out the work would be to engage a suitable PhD candidate to carry out the research with the project being managed jointly by the Professional Standards Unit and the HR Directorate. Since the study was completed, significant changes (including reduction in staff numbers) has led to the decision to postpone the start of the research work temporarily. However it was agreed at the December PMB meeting that there should be a change of direction for this work: the Prisoner Reform Trust and Partners of Prisoners should be approached to assist with the necessary research. It was further agreed therefore, that responsibility for this action would transfer to Beverley Thompson who would update on progress at the next PMB meeting on 6 February. In view of the progress made, it is suggested that the RAG status change to Amber. | Red | Red
7 | MUB | 82 - Prisoners should not be used under any circumstances to assist in the investigation of complaints of racism, or to act as an intermediary between the complainant and the investigating officer. Response: Accepted. The Prison Service Race Equality Plan includes a mediation project, mentioned in the initial response, but this is designed to be an option to resolve conflict and is considered to be consistent with this recommendation. This recommendation is accepted as it does not appear to affect the Mediation project being piloted described in Rec.79 (see 'Parallel Worlds' below on page 18). Mediation is not used as part of an investigation process it is used to resolve conflict with the consent of both parties. It is left open to both parties to decide on an investigation instead of taking part in mediation. No Further Action required. Beverley Thompson | COMPLETED
8 | MUB | 83 - The definition of a racist incident adopted by the Stephen Lawrence Inquiry should be used to identify what constitutes a complaint of racism so that a complaint of racism is one where the action complained of is perceived to be racist by the victim or any other person. Responses: Accepted: as noted in the initial response, the definition of a racist incident adopted by the Stephen Lawrence Inquiry is the one used by the Prison Service. Beverley Thompson | COMPLETED
| Theme: | Community Engagement | Project/ Policy Owner: | Beverley Thompson
| Summary | The project focuses on exploring and looking at ways of developing different vehicles which can support and enhance the Prison's link with external BME communities who can help to enhance Prison Service provision to BME prisoners within our custody. The project will also ensure that the Service is meeting both its general and specific duties under the Race Relations Amendment (2000) Act as well as responding to the recommendations made by both the CRE investigation and those set out in the Mubarek Report.
| Driver | Key Activity | Actions | Milestones | Planned cost: Staff | Planned cost: Other | Project Delivery risk | Progress | R/A/G Status this month | R/A/G Status Last Month
9 | CRE | National Engagement Identify & engage with external BME communities including gypsies & travellers Beverley Thompson/Lynn Barham | PRODUCT 1. Produce a report to address the needs of the gypsy and traveller prisoner population to inform guidance on Gypsy & Traveller prisoners to be issued across the estate as part of a wider raising awareness campaign. 2. Produce an awareness raising pack for prisoners BENEFITS 1. Greater insight into the specific needs of the gypsy and traveller prisoner population. | 1. September 2007 |  | £30K £10K T&S | Low | 1. Findings from research undertaken in October 2007 will form the basis of a promotional campaign celebrating Gypsy & Traveller culture - this will raise awareness for prisoners and staff. Work on initial draft of awareness pack will commence in February 2008. Yvonne MacNamara (Irish Travllers' Movement), is in the process of establishing a sub-group of the Race Advisory Group from different Gypsy & Traveller Groups and Community Organisations. The sub-group will act as a specialist consultative forum for the work REAG are undertaking in this area. This work has been reassessed as RAG Red due to difficulties in establishing the subgroup. | Red | Green |  |  |  |  | RAG assessment centre to have taken place and prospective members to have been identified.
10 | CRE | Advice and Guidance Provide advice and guidance at Area Level to the operational line in relation to community engagement within PSO 2800. Beverley Thompson/Lynn Barham | PRODUCTS 1. Produce guidance on what Community Engagement means for prisoners and how to map current inititives locally. 2. Produce an Area template for Community Engagement mapping returns. 3. Produce a detailed feedback report on current Community Engagement nationally. BENEFITS 1.Will provide "a map" of current community engagement at a national, area and local level. 2.Template will identify specific needs of BME prisoners through the prison's mapping exercise, impact assessment and other monitoring tools 3. The report will identify gaps and best practise for BME prisoners. | 1. July 2007 2. July 2007 3. December 2007 |  |  | Medium | 1 & 2 Guidance & Template completed. 3. Establishments have submitted their mapping exercise returns through Area Office which have been forwarded to Nacro for indepth analysis. A synopsis of findings giving a national overview and identifying the next steps to be taken - this will be produced and disseminated via the REAG website in February 2008. Although there has been a slippage in the evaluation of the mapping due to a family bereavement of the analyst, (this work was due to be completed by Dec 07) - the deadline of Feb 08 for the dissemination of the feedback report to Areas will be met. | Amber | Amber |  |  |  |  | Area template and supporting guidance notes will have been issued to Area Leads for dissemination for returns by mid September 2007. Initial feedback from the REO training and the responses and feedback to the community engagement module.
11 | CRE | "Testing the Market" - pilot models of community engagement Beverley Thompson/Lynn Barham | PRODUCTS 1. Provide a model of Community Engagement for rural & semi rural prisons, taking into consideration the ability of small BME group to deliver the needs of BME groups in prisons: ~ Set up Governance Board ~ Meetings of Governance Board ~ Production of agreed model 2. South West Project to produce a report on local initiatives (such as SW and Isle of Wight projects). BENEFITS 1.Will provide a proven and tested framework for all prisons in rural and semi rural areas to engage with BME communities. 2. Will identify good practice and provide guidance on what works enabling all prisons, regardless of geographical location. to meet the mandatory requirements set out in PSO2800. | 1. Isle of Wight ~ November 2007 ~ Quarterly ~ November 2008 |  |  | Low | ~ Isle of Wight project - The role of Community Engagement Liaison has now been successfully filled. A steering board (first meeting taking place on 28th February), has been set up to discuss progress the agreed measures for each establishment and to check that the current mechanisms are meeting the needs of BME prisoners within those prisons. Governance Board includes representatives from REAG, South Central area, Governors of the 3 prisons and PRENO. ~ South West project - Meeting held with SW Area Manager, Area Diversity Lead and CLINKS to discuss this project and provide an up date to the Area Manager. Work progressing well and in principle the project has been agreed at an Area level. Further meetings between CLINKS and National Body with Fata-He to take place to progress proposal to final stage. Follow up with all parties to take place over the next months. This project is being managed by CLINKS, POPS and S.West Area Office who are currently recuiting an Area Diversity advisor on Community Engagment. Role of REAG is to monitor and report on progress. | Green | Green |  |  |  |  | Finalised project proposal and date for meeting with SW Area Manager to present findings re the CE and the SW Area as well as feedback on the work undertaken to date to resolve the gap in CE work in the Area.
12 | CRE | Outreach Work - Develop partnerships and joint working where appropriate in order to enhance and add value to service delivery to BME prisoners. Beverley Thompson/Lynn Barham | PRODUCTS 1. Produce a quarterly Newsletter which will disseminate models of best practise across the estate. 2. Produce a report on how the private and business sectors can be part of the Community Engagement work of the Prison Service. BENEFITS 1. Up to date information will be provided on what is happening across the estate as well as externally to the service which will enhance their own race equality service provision and will promote the community engagement work already happening within the service to stakeholders and the public. 2. Will open up opportunity to increase community engagement for the Service outside of the voluntary and community sector and will provide an insight into the role that the private and busines sector can play in developing our CE work. | 1. Quarterly 2. March 2008 |  |  | Low | 3rd edition of the quarterly newsletter was produced and disseminated this month across the Estate, to our external partners and through the REAG website. The 4th edition (January 2008) is due to be published in February 2008. Attended external events to raise the profile of community engagement work at the national level: ~ CLINKS Partnership Event for Voluntary Organisations working with Ethnic Minority Offenders ~ Anne Peaker Centre – Multi Culture2 (MC2) to discuss expanding diversity in criminal justice arts provision specifically in relation to BME engagement ~ Run workshops at the Increasing Community Engagement and Social Inclusion for Travellers | Green | Green
13 | CRE | Monitoring & Evaluation Beverley Thompson/Lynn Barham | PRODUCT 1. Report on monitoring and evaluation of Community Engagement initiatives using existing monitoring processes (e.g. PIP & QQ) BENEFIT 1. Will provide an evaluation of what works, what outputs have been successful, what is still needed to be done and what future support is required in relation to community engagement at a national level, Area and local level ensuring best use and the best value of resources. Business as Usual | 1. December 2007 |  |  | Low | The latest QQ (Q2) provided details of some of the Community Engagement work currently taking place in establishments - this will be amalgamated into the mapping evaluation. | [6 empty] | The most recent Quarterly Questionnaire Returns need to be analysed for trends in relation to Community Engagement. Work to be undertaken with Service Delivery and Implementation Team regarding the PIP process and who Community Engagement outputs will be measured within the process.
| Theme: | Race Advisory Group | Project/ Policy Owner: | Beverley Thompson
| Summary | REAG will continue to Chair the Race Advisory Group, which will act as an advisory/consultation body supporting PSMB. The Terms of Reference of this Group will be enhanced to provide external scrutiny and challenge to the Prison Service in its work on race equality and to critique and provide options for improvement of policy and practice on race equality. The group will also advise and support the Prison Service in taking forward work on community engagement with minority groups, particularly Black and Minority Ethnic and Gypsy and Traveller communities and act as an independent consultation forum for Prison Service and NOMS HQ policy leads in the development and race equality impact assessment of policies.
| Driver | Key Activity | Actions | Milestones | Planned cost: Staff | Planned cost: Other | Project Delivery risk | Progress | R/A/G Status this month | R/A/G Status Last Month | Column1
14 | CRE | Develop Race Advisory Group to provide external input to race equality work Beverley Thompson | PRODUCT 1. Commnence and complete recuitment process 2. 1st RAG meeting of new members 3. Regular RAG meetings will be held BENEFIT 1. Independent (of REAG) recruitment of RAG members based on competencies required for the role. Completed: BUSINESS AS USUAL | 1. July 2007 2. July 2007 3. Quarterly |  | £28K | Low | The second induction visit for RAG members took place on the 9th Jan at HMP Wandsworth: the day included the first RAG meeting for the newly appointed RAG group. RAG members have been asked to engage with REAG on the complaints and racist incident project and also take an active role in the review of the race equality programme during 2008. The next meeting has been scheduled for April 3rd 2008 | Green | Green | QTR update next 3rd April
| Theme: | Policy & Performance | Project/ Policy Owner: | Beverley Thompson
| Summary | We will publish a Race Equality Scheme (RES) in line with our legal obligations under the RR(A)A. Going beyond these obligations, we will publish an Annual Report on the RES that sets out our action plan and progress on the management of race equality, as well providing information about how to obtain the impact assessments that have been completed of national policies and establishment functions. These impact assessments will be quality assured. We will ensure that we have effective policy on race equality and accurate monitoring of establishment performance and implementation of the policy, reported quarterly to the Prison Service Management Board, and used to revise the policy where appropriate.
| Driver | Key Activity | Actions | Milestones | Planned cost: Staff | Planned cost: Other | Project Delivery risk | Progress | R/A/G Status this month | R/A/G Status Last Month | Column1 |  |  |  |  | Column1
15 | RES | Drafting and publication of Annual Report on Race Equality Scheme. Includes update on progress on REAP and on programmes of policy and establishment impact assessments. Beverley Thompson/Chris Barnett-Page | PRODUCT 1. Annual report to PSMB 2. Publish report BENEFIT 1.Public demonstation of compliance with RR(A)A2000 Completed | 2007-07-01 | 0.1xD 0.3xF 0.1x G | £15k | Low | PSO 2800 impact assessment published on REAG intranet site. Revised Standard 48 agreed by OPG on 23 May and published on intranet on 11 July. | Green | Green |  |  | Review continues. |  |  | Draft to PSMB in early July for publication by end of July. DONE VP
16 | RES | Quality assurance of establishment impact assessments. Includes completion of QA on final three mandatory areas and training, support and monitoring of Area QA of establishment IA programmes Beverley Thompson | 1. Complete QA of three mandatory areas 2. Training, support and monitoring for Areas Completed: BUSINESS AS USUAL | 1. January 2007 2. Ongoing | 0.1xD 0.3xE 0.2x G | £0k | Low | Support ongoing,. National pictore of progress will be reported to PSMB with QQ returns in February. Review group chaired by Phil Copple considering ways of improving impact assessment process.
17 | RES | Maintenance and review of policy on race equality. Includes: * publication of impact assessment of revised PSO2800; * development of revised Standard 48; * review of PSO2800, including progress on actions derived from impact assessment. Beverley Thompson/Chris Barnett-Page | PRODUCT 1. Publish impact assessment 2. Publish revised Standard 48 3. Complete review of PSO2800 BENEFIT 1. Public demonstration of compliance with RR(A)2000; 2. Measure of establishment compliance with policy; 3. Improved policy | 1. February 2007 2. March 2007 3. June 2008 | 0.1xD 0.3xE | £5k | Low | PSO 2800 impact assessment published on REAG intranet site. Revised Standard 48 agreed by OPG on 23 May and published on intranet on 11 July. Review of first year's performance has commenced. The milestone for the review to be completed has been revised to June 2008, to allow a full data set to be collected and appropriate revisions to be made to PSO2800 Impact Assessment for publication with RES Annual Report 2007-08 in July 2008. | Green | Green | Review of first year’s performance will continue. | Review continues |  |  |  | Revised Standard 48 to be published by end June. DONE BY 11 JULY VP
18 | RES | Maintenance and review of KPT on race equality. Includes: * operational review; * review of SMART, visitor survey and use of MQPL data; * strategic review; * maintenance of IT support. Beverley Thompson/Chris Barnett-Page | PRODUCT 1. Complete operational review 2. Complete review of SMART, visitor survey and use of MQPL data 3. Agreement by PSMB 4. Implementation BENEFIT 1. Improved data integrity 2. Improved KPT measure | 1. March 2007 2. September 2007 3. November 2007 4. April 2008 | 0.1xD 0.4xE 0.3x G | £15k | Low | Following operational review improved guidance on data capture was issued in June 07. Review of SMART, the Visitor Survey and use of MQPL data completed. Strategic review cancelled following consultation with DG. Results of review and proposed way forward agreed by Area Managers and DDG in November 2007. Final clearance by DG awaited. Preparation work on implementation has commenced. | Green | Green
19 | RES | Quarterly report on establishment progress to PSMB. Includes: * review of quarterly questionnaire; * improved reporting on progress on recommendations from external bodies, establishment REAPs and impact assessment programmes. Beverley Thompson/Chris Barnett-Page | 1. Complete review of QQ for implementation in Q4 2. Revised reporting arrangements in place for Q4 COMPLETED: BUSINESS AS USUAL | March 2007 | 0.1xD 0.2xF 0.3x G | £10k | Low | Revised and improved reports now provided to PSMB and Area Managers, including comparison of performance by Areas. | [7 empty] | Presentation of data analysis to PSMB on 18 June. Reports to Area Managers by end June.
20 | CRE | Ensure effective data collection & analysis to support monitoring of impact of policies on prisoners of all racial groups This principally concerns the development of IT through liaison with NOMIS project. Beverley Thompson/Chris Barnett-Page | PRODUCT National snapshot of of impact of policies on prisoners of all racial groups. BENEFIT Improved ethnic monitoring capacity | End April 2008 | 0.1xE 0.1x G | £0k | High | Method for making maximum use of data recorded on LIDS identified. Work under way to collect this data. Temporary member of staff has been recruited to collate and analyse the data. In view of progress made, it is proposed that the RAG status should be changed to Amber. | Red | Red | Work on producing national snapshot by aggregating local SMART data will begin. | A proposal for work to improve data capture on LIDS will be submitted. | A proposal for work to improve data capture on LIDS will be submitted.
21 |  | Develop and maintain a database collating estabilshment performance information from a range of sources including HMCIP, KPT etc and provide a monthly report on areas of concern to Service Delivery Implementation Team (REAG) | PRODUCT 1. Develop database 2. Input data 3. Maintain database 4. Produce monthly report | 1. May 2007 2. August 2007 3. Monthly from August 2007 4. Monthly from October 2007 |  |  | Low | Retrospective data input completed. First monthly report produced. | Green | Green | Improved monthly report to be produced, following feedback on first attempt. | First monthly report to be produced. | First monthly report to be produced.
| Theme: | MANAGING RACIST BEHAVIOUR | Project/ Policy Owner: | Beverley Thompson
| Summary | REAG have set up a Strategy Group comprising of representatives from the Prison Service (operational and non-operational) and other Criminal Justice Agencies to work together to produce a strategy for addressing the attitudes and behaviours of racially motivated offenders and those prisoners that display racist attitudes whilst in custody. The group will do this through the development of appropriate & effective identification of racist prisoners, idenfication of good practise and what elements can be used by the Service, development of appropriate training to increase the confidence & competence of staff working with racist prisoners, and the application of appropriate evaluation methods to assess whether the strategy is producing effective outcomes.
| Driver | Key Activity | Actions | Milestones | Planned cost: Staff | Planned cost: Other | Project Delivery risk | Progress | R/A/G Status this month | R/A/G Status Last Month
22 | CRE | Develop processes, for use by staff, to identify offenders who may hold racist attitudes. Beverley Thompson/Miloni Patel | PRODUCT 1. Develop a method to provide information on detecting racism. 2. Devise a procedure by which this information can be monitored and actioned within establishments 3. Undertake pilots in HMP Belmarsh, Holloway & Wandsworth 4. Produce reports following evaluation of pilots 5. Roll-out information nationally BENEFIT 1. Staff to be more confident & able to identify prisoners who hold racist attitudes 2. Staff will be more likely to report potentially racist prisoners. Establishments will have a structured process in place to manage the above. 3 & 4. Ensure confidence in the proposed procedure. | 1. June 2006 2. July 2006 3. September 2006 4. November 2007 5. March 2008 |  | £10K £10k T&S | Medium | The pilot phase of this work has now concluded. It has been decided that this work will be rolled out nationally via a written brief and information for staff at all establishments. This will be completed by March 2008. | Green | Green
23 | RES | Review current practices for addressing racist offenders to determine what aspects can be used in the Prison Service Strategy Beverley Thompson/Miloni Patel | PRODUCT 1. Research existing programmes/methods of working with racist offenders across other criminal justice agencies 2. Identify components of the above that can be used in a Prison Service approach to address the attitudes of racist prisoners 3. Using the above develop an awareness raising package for use with low risk prisoners 4. Test package BENEFIT 1 & 2. Utilising existing practices which have a proven level success. 3. Providing the Prison Service with a resource to effectively manage and address racist attitudes and behaviour. | 1. 1 March 2007 2. 1 October 2007 3. 1 January 2008 4. Feb/March 2008 |  |  | Medium | Those prisoners assessed as high risk will be managed by prison security departments and existing prison management systems (e.g. IEP, adjudications) will be used to manage the medium risk group. The low risk package has been completed and this will now be amalgamated into a larger educational training pack that can be delivered to all prisoners who will achieve a qualification in Race Equality upon completion. This educational pack is due to be tested in the Wales area Feb-March 2008. SEE ROW 30 BELOW | Green | Green
24 | RES | Conduct pilots of the final toolkit of interventions Beverley Thompson/Miloni Patel | PRODUCT 1. Pilot the final toolkit in HMP Belmarsh, Holloway, and Wandsworth for a period of 5 months 2. Roll-out strategy BENEFIT Ensuring implementation of the toolkit is effective and viable. | March 2008 |  |  | Medium | Rather than a toolkit of interventions this work can better be described as a strategy for identifying and managing racist behaviour. The strategy consists of the ‘detecting racism’ and classification procedure, management of high and medium risk prisoners by security department and prison management systems, and the educational training pack for prisoners. The strategy will be rolled out in March 2008. | Green | Green
25 | RES | Develop a training programme for staff working with racist offenders Beverley Thompson/Miloni Patel | PRODUCT 1. Conduct a needs analysis, by way of focus groups with staff. 2. Develop a training package(s) for staff working with those prisoners identified as racist. This will be tailored to those working with prisoners classified as 'high', 'medium', and 'low'. BENEFIT Analysis will determine the gaps in knowledge that staff may have. | 1. 1 September 2007 2. 1 January 2008 |  |  | High | The low risk pack has now been amalgamated with an educational training programme for prisoners, to be delivered by educational departments. As such the training element is no longer a significant concern given that teachers will already hold appropriate qualifications to deliver this work. It is planned to issue practice guidelines alongside the pack to address any deficits in knowledge in terms of the race element. SEE ROW 30 BELOW | Green | Green
26 | RES | Deliver area briefings to staff on the 'Detecting Racism' procedure and the low risk package in preparation of a national roll out of the strategy for managing prisoners with racist attitudes and behaviours Beverley Thompson/Miloni Patel | PRODUCT 1. Provide information to relevant staff so that they know what is expected of them with regards to implementation of the strategy 2. Liaise with Security Policy Group to request instructions are sent to local security departments with regards to implementing the 'Detecting Racism' procedure. BENEFIT 1. Training needs of this group will be met, enabling them to effectively manage racist prisoners. 2. Mandatory instruction from SPG will ensure effective implementation of the 'Detecting Racism' procedure | 2008-04-01 |  |  | High | This will form the national rollout of the strategy and will be completed by March 2008. | Green | Green
27 | RES | Develop systems to evaluate and monitor the effectiveness of the strategy following implementation Beverley Thompson/Miloni Patel | PRODUCT A method of monitoring will be developed to ensure delivery of the strategy meets expected requirements. This will include factors to indicate whether the strategy is effective in managing racist prisoners. BENEFIT Ensure that systems are in place to monitor the effectiveness of the strategy. | 2008-02-01 |  |  | High | Due to the change in the scope of the work a low level approach to evaluation is appropriate. This is likely to be in the form of post course questionnaires (following completion of the educational training), inclusion of requests for feedback in the Quarterly Questionnaire (not every quarter), and analysis of HMCIP reports to determine the extent to which establishments have implemented the strategy. SEE ROW 30 BELOW | Green | Green
| Theme: | Service Delivery & Implementation |  | Project/ Policy Owner: |  | Beverley Thompson
| Summary | The Service Delivery & Implementation Team (SDIT) will focus on enhancing the delivery of race equality outcomes in establishments. It will use PIP as one method of driving up performance and support Area Managers in their aim of ensuring race equality is appropriately implemented in their prisons. SDIT will also work with the Policy & Performance Development Team to identify indicators which suggest establishments either need more support or are exampling best practise. SDIT will also design induction interventions for prisoners, which will help ensure prisoners are aware of their responsibilities whilst in custody.
| Driver | Key Activity | Actions | Milestones | Planned cost: Staff | Planned cost: Other | Project Delivery risk | Progress | R/A/G Status this month | R/A/G Status Last Month | Column1 |  |  |  | Column2 | Column1
28 | CRE | Provide support (via Efficency & Consultancy Group) to the Performance Improvement Process (PIP) by: Attending establishments to assess their performance against policy/legislation requirements. Beverley Thompson/Richie Dell | PRODUCT 1. Conduct assessment and provide a report which measures progress on implementing race equality using PSO2800 and 2007 revised standards. Eight areas have been identified for the 06/07 reporting year. 2. Report on Area Diversity Leads' attendance to at least one establishment in their area in order to shadow SDIT members on PIP assessments. 3. Report on progress against previously reported required actions and report through the PIP process. BENEFIT 1. Will enable oversight of the implementation of PSO2800. 2. will support the up-skilling of ADL in carrying out assessments. 3. Will provide a progress report on previously reported recommendations. | April 2008 |  | £10k T&S | Medium | The Service Delivery Team has completed 12 PIP assessments. This completes the initial PIP assessments, including one assessment which was not on the original agreement (HMYOI Deerbolt) | Green | Green |  |  | Complete HMP Risley’s PIP assessment. | Complete HMP Pentonville’s PIP assessment. | Complete PIP assessment at HMYOI Deerbolt | Continue with recruitment campaign in order to obtain staff to complete this target.
29 | CRE | Conduct health checks as requested by Area Managers Beverley Thompson/Richie Dell | PRODUCT 1. Conduct health checks and prioritise the areas raised by the Area Manager. 2. Report on findings (for the Area Manager) within 14 days of completion. 3. Provide areas of good practice to REAG communications for disemminating to the field - see Communications theme. BENEFIT 1. Will support individual concerns /good practice within establishments. 2. Provide recommendations to Area Manager on findings. 3. Ensure cascading of good practice to all establishments from HQ. | As requested |  | £10k T&S | Medium | All assessments completed have been communicated to Strategy & Performance Group and the Area Offices. | Green | Amber | Continuing working with all establishments and respond to any other Area Manager’s requests for support. | Continuing working with all establishments and respond to any other Area Manager’s requests for support. | Continuing working with all establishments and respond to any other Area Manager’s requests for support. | Continuing working with all establishments and respond to any other Area Manager’s requests for support. | Continuing working with all establishments and respond to any other Area Manager’s requests for support. | Continuing working with both establishments and respond to any other Area Manager’s requests for support.
30 | RES | Design a modular race equality training pack for prisoner induction and at future training events within sentence length. | PRODUCT 1. Develop an induction training module for prisoners 2. Produce a further training pack (7 modules) of race equality information for prisoners BENEFIT 1. Standard approach to race equality induction, for prisoners, will be produced. 2. Increased prisoner cultural awareness. | August 2007 March 2008 |  | £9k T&S | Medium | Following further consideration, it was agreed that the work on managing racist behaviour work would form an element of, and run concurrently with the development of the modular race equality training pack for prisoner induction. It was agreed that this work would have a milestone of March 2008: ~ the modular training pack (including managing racist behaviour), is currently being piloted in the Wales Area and on schedule to be completed by end March 08; ~ A national induction DVD will be produced to meet this requirement - work is ongoing on its production. | Green | Green | Meet with Head of Learning Skills in Wales to organise pilot and set up accreditation. Contact the Head of learning skills to determine how the pack fits into OLASS. | Meet with Head of Learning Skills in Wales to organise pilot and set up accreditation. Meet with Head of learning skills at Regime Services to determine how/if the pack fits into OLASS. | Continue to develop part 2 of the objective | Continue to develop part 2 of the objective | Continue to develop part 2 of the objective | Continue with recruitment campaign in order to obtain staff to complete this target.
31 | CRE | To act on information received by REAG’s monitoring indicating areas of concern emanating form internal and external drivers. | PRODUCT 1. Conduct assessment and provide a report on areas of concern. 2. Provide support to address these areas. BENEFIT 1. Provide a cohesive approach to rectifying areas of concern. 2. Sharing good practice from other areas (e.g. CJS, Health Service) with the prisons identified as having areas for improvement. BUSINESS AS USUAL | As required |  | £9k T&S | High | A performance database has now been devised by the Policy & Performance Team within REAG. The Service Delivery Team is now able to monitor establishments where there may be cause for concern and contact the establishment to offer REAG support |  |  | Using the new database SDIT will assess performance of establishments and initiate contact. | Using the new database SDIT will assess performance of establishments and initiate contact. | Using the new database SDIT will assess performance of establishments and initiate contact. | Nil, awaiting completion of monitoring database in June 07. | Nil, awaiting completion of monitoring database in June 07. | Nil, awaiting completion of monitoring database in June 07.
| Theme: | Training | Project/ Policy Owner: | Project/ Policy Owner:
| Summary | Following the separation of responsibilities for staff diversity and equality from those for prisoner-orientated race equality matters, the first step in developing training provision in the former is to develop appropriate guidance for establishments on how to develop staff diversity training strategies (a training strategy covering prisoner race equality matters is extant) It is possible that further specific key activities related to staff diversity and equality training will be identified as a result of this work.Additionally, TDG have responsibility for implementing four recommendations arising out of the Mubarek inquiry: three relate to adjustments to POELT training and one to dealing with the interpretation of evidence as part of training for those conducting investigations. This will ensure that this provision is properly fit for purpose. REAG will ensure that both REAT and REO training are kept up to date in order to support the implemenation of policy and legal obligations in establishments. Staff Diversity Training Strategy which will outline a prioritsed programme of awareness raising for different target audiences. A series of modules supplemented by revised guidance will make staff aware of the Prison Service's commitment to diversity and the benefit of employing a diverse workforces as well as our legal commitments.
| Driver | Key Activity | Actions | Milestones | Planned cost: Staff | Planned cost: Other | Project Delivery risk | Progress | R/A/G Status this month | R/A/G Status Last Month
32 | CRE | Produce guidance to help establishments develop diversity training strategies; identifying and drawing on existing good practice; and the selection and training of trainers Ian Gray/John Nicholson | PRODUCT 1. Develop training strategy 2. Agree list of priority areas and delivery plan | 1. November 2007 2. March 2008 | tbc, resource transfer from REAG needs to be settled | tbc, resource transfer from REAG needs to be settled | High | A draft diversity training strategy has been developed in conjunction with Learning & Development. In conjunction with REAG and Learning & Development the diversity content of POELT was identified as a priority area for action. Following visits to view the current diversity content of POELT, and a meeting with L & D, objectives have been drafted and circulated for agreement. A resource needs to identified to take this work forward this financial year. As part of the action plan for tackling unacceptable behaviour and harassment, work is in hand for the development of a DVD covering a range of diversity issues. This will be available to trainers for local delivery early in the new financial year. | Green | Green |  |  |  |  | A detailed draft Strategy is to be prepared for consultation during August 2007. The proposals will include a series of equality and diversity learning packages as well as a review of existing training to ensure that key messages are threaded through existing learning and delivery objectives | Meeting with Learning & Development planned for after Board presentation on 11 June. Draft diversity training strategy will be produced by 30 June.
33 | CRE | Develop a specific race and diversity package and refresher course for staff identified as having a specialised learning requirement. Ian Gray/John Nicholson | PRODUCT 1. Develop training strategy 2. Agree a list of priority areas and delivery plan |  | tbc, resource transfer from REAG needs to be settled | tbc, resource transfer from REAG needs to be settled | High |  | Green | Green | [5 empty] | Meeting with Learning & Development planned for after Board presentation on 11 June. Draft diversity training strategy will be produced by 30 June.
34 | MUB | 63 - The part of the basic training course for new prison officers which focuses on the development of their interpersonal skills should be reviewed in the light of this report and the lessons to be learned from Zahid's murder. In particular two of the key attributes required of the prison officer should be stressed. They are the ability to pick up on what is happening on the wing, which prisoners pose a risk to other inmates, and what prisoners might be worried about, and the ability to earn the respect of the prisoners on the wing so that they are prepared to confide in them without fear of it getting out. Response: Accepted All interpersonal skills modules are currently being reviewed to reflect this recommendation. Initial observation is that it links in well with dynamic security, which will also be looked at as part of the review. However, this work ties in closely with that of recommendations 64 and 80, and a decision has been made to delay the piloting of this material until the final consultation with BME ex-offenders during and after the production of the training DVD. Stacey Tasker | PRODUCT 1. Refine the Prison Officer Entry Level Programme to ensure that the requirement for staff to be able to pick up on what is happening on the wing and the ability to earn the respect of the prisoners on the wing, are taken into account. Complete. | Revised programme in place April 2007. | No additional cost | No additional cost | Low | Pilots of the revised course containing the recommended components are complete and the Trainer manual has been printed. This completes the requirements of this recommendation.
35 | MUB | 64 - Ex offenders should be used to give trainees an insight into prison life from the perspective of prisoners. Response: Recommendation requires further consideration. The Prison Officer Entry Level Training is modular and involves time on prison wings with offenders. Enquiries and research into the feasiblity of recruiting and training of ex-offender to assist with the POELT course - advice awaited from advisor to Mubarek Inquiry on this issue. Consideration has been given to producing a DVD (as with the proposal at recommendation 80), as a method of providing staff with an awareness of the prisoner’s perspective. Stacey Tasker | PRODUCT 1. Conduct a feasibility study 2. Produce a DVD as a method of providing staff with an awareness of the prisoner perspective COMPLETED. | 2007-04-01 | £50k | £50k for DVD | Low | Meeting took place with REAG on 26/10/07. It was agreed that, although the current DVD falls short of meeting Mubarek recommendation 81, it does meet the requirements of recommendation 64 and could be used as appropriate to underpin diversity training and security training in POELT. At the REAP PMB meeting on 6 November, the board agreed that this recommendation can be considered completed.
36 | MUB | 80 - The diversity training which prison officers receive as part of the basic training should stress the need for them to put themselves in the position of BME prisoners and see things from their point of view. They should be told about the techniques they can use to develop that skill. Response: Accepted. A comprehensive review of the diversity material has taken longer than expected, research is now complete and a curriculum development focus group is involved in ensuring this material meets the requirement of the report. Stacey Tasker | PRODUCT 1. Review and refine POELT | Full implementation of revised curriculum by April 2007 | No additional cost | As above | Low | POELT ‘week 5’ (establishment based learning) guidelines and reflective journal have been amended to incorporate the need for students to have the opportunity, wherever possible, to meet and talk to BME prisoners. REAG, the POELT Curriculum Development manager and the Training Policy Unit are working together to drive forward production of a new DVD which will accurately reflect prisoners’ points of view and meet this recommendation. An updated action plan for this work will presented to the Board on 6 Feb 2008. | Red | Red
37 | MUB | 81 - The training of any officer responsible for investigating complaints of racism should stress that corroborative evidence of a complaint, though desirable, is not essential. Officers should be reminded of the need to guard against falling into the trap of seeing as decisive the existence of a possible racially neutral reason for treatment which would otherwise be discriminatory. Accepted. A pilot Investigations course was run in January 2007 and further revisions are currently being made. There will be a further pilot, incorporating the revisions, in March. Stacey Tasker | PRODUCT 1. Review and update the investigations training portfolio to include provision for training on the investigation of complaints of racism. | Training re-launched December 2006 | No additional cost | No additional cost | Medium | A meeting took place on 17 January involving the Curriculum Manager, an Investigations course trainer, the Policy Lead and representatives from REAG which resulted in a clear action plan being produced. Aim is for all necessary work and reinstatment of course to be undertaken by end Feb 2008. An updated action plan for this work will be presented to the Board on 6 Feb. | Red | Red
38 |  | Oversee the national implementation of Race Equality Action Team (REAT) members training , incorporating the SAR process. Beverley Thompson/Richie Dell | PRODUCT 1. Collect data on training timetables 2. Conduct tutor assessments 3. Undertake tutor meetings to obtain feedback on training progress 4. Undertake tutor meetings to advise on changes to training material 5. Meet the requirement of the current SAR Action Plan BENEFIT 1. Enables the SAR process to be implemented. 2. Ensures the quality of delivery 3 & 4. Provides effective two way communication between tutors and REAG | 2008-10-01 |  |  | Medium | REAT training continues to be rolled out across the service with most areas having trained some of their REAT. Begin to put SAR action plan into place. Meet with Learning & Development to decide how to hand over the administration of training to them. | Green | Green | continue to work with training delivery team at newbold revel to facilitate hand over of training as soon as possible | Continue to observe trainers and update SAR action plan. | Attend SAR QA inspection at HMP Lindholme | Nil: Continue to monitor SAR feedback | Provide another training for trainers course in July07 and continue to implement the SAR process. | Produce draft SAR report for July’s submission. Provide one training for trainers course to meet requests from area office’s.
39 |  | Develop a training course for Race Equality Officers (REO). Beverley Thompson/Richie Dell | PRODUCT 1. Design and pilot new REO training 2. Amend training on completion of pilot 3. Introduce new REO training. BENEFIT Enhance competencies of REOs COMPLETED. | 2007-09-02 |  | £10k | Medium | One REO course run at Pentonville | Green | Green | Continue to run course. Liaise with training delivery team at newbold revel to facilitate hand over of training as soon as possible | Continue to run course. |  |  | Run pilot REO course and amend training resource as necessary. | To complete draft training pack and to arrange a pilot in a Service area.
| Theme: | Retention & Progression | Project/ Policy Owner: | Nick Pascoe/Ian Gray
| Summary | Better understanding of retention issues regarding BME staff
| Driver | Key Activity | Actions | Milestones | Planned cost: Staff | Planned cost: Other | Project Delivery risk | Progress | R/A/G Status this month | R/A/G Status Last Month
40 | CRE | Review Prison Service retention and progression procedures. Ian Gray
41 | CRE | Analyse findings of the outsourced exit survey pilot Nick Pascoe/Lindsay Wilson | PRODUCT 1. Commence pilot 2. Analyse and produce report on findings | 2007-05-01 | External provider | £15,450 +VAT | Medium | London Area commenced the pilot (12 months) from May 2007. The exercise is being undertaken by an external provider. A full analysis and evaluation will take place at the end of the pilot. The first quarter of findings have been released however only a very low number of surveys were returned to the provider during this period. Full presentation on the findings so far and requirements of the contract to be given at the next PMB meeting (6 November) | Red | Red
42 |  | Establishments to review their positive action steps with regard to the recruitment and retention of under-represented ethnic groups Ian Gray | Submit report to PSMB | 2007-11-01 |  |  |  | Opportunities are being taken to use the branding developed for the South Central recruitment campaign, to raise the profile of the Service through specialist advertising media. 2nd Quarter report of the London exit survey pilot has just been received. As with the 1st Quarter report, the number of leavers appears low and this is being investigated. The main areas of negative feedback were opportunities for career development and promotions, and overtime, though these were not BME specific. | Green | Green
| Theme: | Catering | Project/ Policy Owner: | Simon Boddis
| Summary | Caterers have a responsibility to provide a range of meals and food items to meet the needs of a diverse prisoner population. Menu choice is largely an establishment decision but how this is achieved and to what standard is outlined in PSO 5000 (the Catering Manual). In order to achieve this goal caterers have to be able to buy food to appropriate specifications. The new food contracts will enable this to occur and will include a set mechanism to review specifications and add to the product list. Monitoring to ensure that catering in prisons meets religious, cultural and ethnic dietary needs takes place on a number on a number of levels. Within prisons systems should be in place to ensure meals offered to prisoners reflect, as far as possible, prisoners religious, cultural and ethnic dietary. External monitoring is undertaken by Area Catering Managers and through Standard Audits.
| Driver | Key Activity | Actions | Milestones | Planned cost: Staff | Planned cost: Other | Project Delivery risk | Progress | R/A/G Status this month | R/A/G Status Last Month
43 | CRE | Ensure the new grocery contract delivers food commodities to specifications which will enable caterers to meet the diverse needs of the prisoner population and gain widespread agreement and buy-in for the specification that underpins Halal products used in producing meals for prisoners. Simon Boddis | PRODUCT 1. New contract due to start May 7. 2.Draft and issue Halal standard to help inform food specifications. 3. Frozen food contract due to be let / extended in August 08. | May 2007 June 2007 August 2008 |  |  |  | ~ Monthly meetings are held with HMPS main food supplier, 3663, Yearsley, NH Case, to discuss products, deliveries etc. ~ The frozen food and meat contract (including Halal) has been extended and is due for renewal during 07/ 08. Target date July/August: this includes the supply of food commodities for staff messes and Prisoner retail. ~ The delay in the frozen meat and poultry contract has not detracted from the need to offer reassurance that the Halal products assured provenance: the new Halal Standard has been furnished early to the incumbent contractors to purchase against. CPU await feedback from the contracted supplier base on the ability to procure product to specification which is affordable for the Service. ~ PSO 5000 (the Catering Manual) and the assoc'd Performance Standard have been re-drafted and consultation has taken place. This has been approved to go forward to OPG to be dealt with in January 2008. | Green | Green |  |  |  | Grocery contract will continue to be monitored to evaluate full effects on prison budgets.
44 |  | Area Catering Managers will continue undertaking routine monitoring, maintenance and development of local practice and process. This is a significant part of ensuring adherance to PSO 5000 (the catering manual) and that performance standards are adhered to - this is also a mechanism to help spread good practice and help local caterers develop Simon Boddis | [5 empty] | Ongoing monitoring of menu content, catering practice and process in place is carried out by Area Catering managers during operational visits. Reports are submitted, where required, following establishment visits. Appropriate actions are pursued by the establishment. | [5 empty] | Progress will continue with the tender/ extension to the chilled and frozen food contract
| Theme: | Mubarek Recommendations | Project/ Policy Owner: | Ann Beasley, NOMS, Digby Griffith, Ian Blakeman, Gill Brigden, Richard Bradshaw, Beverley Thompson
| Summary | The Mubarek report does not make easy reading, containing as it does important recommendations for the Prison Service and pointing to a range of failings. Acceptance of the recommendations below commits us being very honest in facing up to the very critcal picture of the Service while recognising the progress made in the last six years. In taking forward the recommendations, and at their request, we will work with the Mubarek family and the newly formed Mubarek Trust set up in Zahid's memory. Many of the recommendations of the Mubarek report are owned by NOMS. REAG will liaise with them as necessary in delivering and monitoring the work set out below.
| Driver | Key Activity | Actions | Milestones | Planned cost: Staff | Planned cost: Other | Project Delivery risk | Progress | R/A/G Status this month | R/A/G Status Last Month | Column1 |  |  |  | Column2 | Column1
45 | MUB | RESOURCES 2. The Prison Service should review whether the resources currently available to it might be better deployed towards achieving this goal, without compromising standards in other areas, and should set a date for realising this objective. Response: Accepted. The proposed review was carried out as a matter of high priority and completed in August 2006. It concluded, however, that redirection of resources on the scale needed to achieve elimination of enforced cell sharing would have unacceptable consequences, particularly to standards of prisoner care and rehabilitation.Assessed as completed in August 2006. Ann Beasley | COMPLETED |  | None | None
46 | MUB | 18. As soon as is practicable, the Prison Service should assess the popularity of the bolted-down furniture made from white wood which is currently being trialled. It should then formulate a policy about the most appropriate form of furniture for use in cells, balancing the need to keep prisoners from their cellmates against the need for prisoners to live in cells which have a measure of homeliness, and taking into account prisoners' preferences and cost. Response: Accepted. The Prison Service has concluded that whitewood furniture should be adopted as the standard suite of cell furniture, except for cells holding prisoners at high risk of suicide or self-harm. Whitewood furniture, already installed in 2,100 cells, will be installed throughout the estate as the current furniture becomes due for replacement at the end of its normal life-cycle. As the initial response made clear, such consideration has already taken place, and concluded that, since a full cell search will always include a search for weapons and other illicit items, there should be no need for a separate search for weapons. Ann Beasley | COMPLETED |  | None | None |  | The review has been completed. White wood furniture is to be adopted as a standard for replacement. ESS are supplying white wood furniture to all new accommodation where Home Office Custodial Property Service have identified is is required. Completed August 2006
47 | MUB | YOUNG OFFENDERS 16. Conduct a review of whether the advantages of holding young offenders on the same wing as adult prisoners outweigh the disadvantages, and make recommendations of whether the practice should be extended to other establishments. Accepted. NOMS/Ian Blakeman | PRODUCT 1. Carry out visits to establishments 2. Analyse data 3. Write report REVIEW COMPLETED - FURTHER ACTION BY NOMS | 1. April 2007 2. June 2007 3. December 2007 | £60k | £20k (T&S) The T&S for this project is an unfunded pressure. | Medium | The review by W&YPG has now been completed and this project can be closed off. The review and its recommendations made to NOMS as future policy holder, has been endorsed by Michael Spurr, DDG, who has passed the review to Paul Hindson, Offender Management Team at NOMS. |  |  |  | First draft for internal submission to W&YPG completed by end October. Internal consultation and drafting scheduled for completion by end December 2007. Report will then got to Michael Spurr for onward submission to NOMS as future policy lead. |  | Further consultation and data analysis work prompted by stakeholder consultation event and report writing. |  | Initial data analysis in preparation for report writing
48 | MUB | 17. Clarify the legality of whether young offenders can be held with adult offenders. Requires further consideration. NOMS/Ian Blakeman |  |  |  |  | Medium | The review considered and made recommendations on Rec. 17. This recommendation was de-scoped from the review as NOMS had obtained their own legal advice. However the review recommended that NOMS evaluate the advice obtained and operationalise that advice to provide clarity for the Prison Service and establishments. | [6 empty] | Stakeholder Consultation Event 25/07 | Planning of stakeholder consultation
49 | MUB | CELL SEARCHES 19. The Prison Service should consider whether dedicated searches of cells for concealed weapons would be tantamount to a full cell search. Digby Griffith/George Houghton | COMPLETED |  | None | None |  | This was considered by the head of prison service security group. He confirmed that a weapons search would constitute a full search. No further action required.
50 | MUB | 20. In any event, the Prison Service should assess the resource and security implications of less frequent but random fabric checks against more frequent and more random full cell searches, bearing in mind that different strategies may be required for different establishments. Accepted. The National Security Framework was introduced in 2002, provides for a flexible searching strategy which allows individual prisons to create their own local searching strategies. The searching and frequency elements of the National Security Framework will be reviewed in the light of the Mubarek report. Digby Griffith/George Houghton | PRODUCT 1.Revised National Security Framework (PSO1000) and Local Security Strategies BENEFIT 1. Standardisation in searching procedures used across the estate. 2. Informed local searching strategies agreed by Governor and Area Manager 3. Improved consistency in searching practices. | 2007-08-31 | None | None | Low | Following Ministers' agreement that routine fabric checks should not be reduced as there could be security implications and OPG's direction that governors views should be obtained on if and how fabric checks could be reduced to make time for more detailed cell searches, a questionnaire has been developed that will be piloted and then report back to OPG in June 2008. Work to restart in February 2008. Approach agreed with Head of REAG. | Green | Red | Survey prepared for prisons to complete. Pilot survey February 2008 Full survey March/April 2008 To OPG June 2008 | Survey prepared for prisons to complete but awaiting decision from Ministers on efficiency proposals to reduce Fabric Checks. Until decision known this work cannot be replanned | Dependant on announcement by Board of future efficiency strategy | Awaiting outcome of senior operational management consideration of reducing frequency of fabric checks as an economy measure to live with a reduced budget
51 | MUB | 21. Senior officers should ensure that their staff know how to carry out fabric checks. They should ensure that officers realise that in order to check the walls of a cell, it will be necessary to look behind or under the furniture next to them. If that can only be done by moving the furniture, the furniture should be moved. If in the course of doing so they discover that the furniture is broken, they should check whether any parts of it could be used as a weapon. Accepted. All prison Officers receive searching training as part of POELT, this is supported by NSF guidance. Audit processes check procedure and performance. Digby Griffith/George Houghton | PRODUCT 1.Revised National Security Framework (PSO1000) and Local Security Strategies BENEFIT 1. Standardisation in searching procedures used across the estate. 2. Staff more aware of what is expected of them in carrying out this work 3. Improved consistency in searching practices. COMPLETED | 2007-08-31 | None | None | Low | Amendments to NSF (PSO 1000) issued issued under PSI 30/2007
52 | MUB | 22. An establishment's written cell-searching strategy should require each cell to be fully searched at least once in every three months. Senior officers should ensure that full cell searches are taking place as regularly as the strategy requires. Returns showing which cells have been fully searched, and when, should be submitted monthly. The department which is supposed to scrutinise the returns should do so speedily, and notify the senior officer of the unit and its principal officer if that is not happening. Digby Griffith/George Houghton | PRODUCT 1.Revised National Security Framework (PSO1000) and Local Security Strategies BENEFIT 1. Standardisation in searching procedures used across the estate. 2. Informed local searching strategies agreed by Governor and Area Manager 3. Improved consistency in searching practices. | 2007-08-31 | None | None | Medium | See comments on recommendation 20 for this project. | Amber | Green |  |  |  | Awaiting outcome of senior operational management consideration of reducing frequency of fabric checks as an economy measure to live with a reduced budget
53 | MUB | PRISONER RECORDS 34. The list of prisoners convictions sent to the prison should include a short statement of the facts of each offence and the charges the prisoner is facing. Accepted in principle. Digby Griffith/Bob Waterman | PRODUCT 1.Develop procedure to ensure immediate notification to receiving prisoner of current offence. 2. Pilot revised PER form BENEFIT 1. Better and informed reception process 2. Potential problems identified easier and earlier. | 1. September 2007 2. January 2008 |  | likelihood of IT hardware costs | Low | Linked to Mubarek Recommendation 50 based upon the introduction of the PER form. | Green | Green | Start Pilots –March 2008 |  |  |  |  | Meeting arranged for 6 June for Security Group on this issue. Then an initial approach to ACPO seeking advice on how to progress this issue
54 | MUB | 35. The Police National Computer should be linked to the whole of the prison estate. In the meantime, any intelligence the police may have about prisoners which could affect their management in prison should be sent to the police liaison officers for the establishments at which the prisoners are being held. A decision can then be made whether the intelligence can be disseminated widely within the prison or given to a governor for their eyes only. Digby Griffith/Bob Waterman | PRODUCT 1.HMPS access to PNC BENEFIT 1. Wider NOMS accreditation to access PNC 2. Full compliance with legal requirements by HMPS/NOMS 3. HMPS have greater ability to update information on PNC for other CJS PNC users to access 4. Greater PNC access (but this is potentially compromised if funding becomes an issue). | 2007-09-01 |  | likelihood of IT hardware costs | Medium | Delay in consideration of application by ACPO now confirmed. Security Group seeking assistance from Police Advisers Section to intercede with ACPO and progress the application. Milestone currently not known. | Amber | Amber | Delay in consideration of application by ACPO now confirmed. Security Group seeking assistance from Police Advisers Section to intercede with ACPO and progress the application |  | To again press for a decision from ACPO. | ACPO consideration delayed (due to unavailability of key ACPO personnel) to September 2007 |  | Letter sent from Helen Edwards to all NOMS units and responses evaluated by Security Group
55 | MUB | 38. Prisoners should not be admitted to a wing without their current wing file save with the permission of a governor or the approval of the night orderly officer. Important entries should be made in red. Gill Brigden | COMPLETED |  | None | None |  | Accepted. PSI 36/2006 issued 27 November 2006
56 | MUB | 40. All establishments should have a procedure for notifying wings in writing that a prisoner is currently charged with or has been convicted of an offence under the Protection from Harassment Act 1997. Gill Brigden | COMPLETED |  |  |  |  | Accepted. This requirement is already in force, but a reminder of the relevant procedures will be included with the guidance issued in response to recommendations 38, 45, 47, and 48. PSI 36/2006 issued 27 November 2006. This is also included in C-NOMIS alerts.
57 | MUB | 45. The senior officer on a wing should ensure that information arriving on the wing about a prisoner is recorded in the wing observation book. Particularly important information should be in red. When coming on duty, staff should read any entries in the wing observation book made since they were last on duty. Gill Brigden | COMPLETED |  | None | None |  | Accepted: PSI 36/2006 issued 27 November 2006.
58 | MUB | SECURITY 41. Each security department should establish a proper system for vetting security files to ensure that they are read by the end of the working day following their arrival, that any relevant information is relayed in writing to the wings and that a record is kept of who vetted them with the date and time. Digby Griffith/George Houghton | COMPLETED |  | None | None |  | Accepted. This is already normal practice, but a reminder to staff will be issued in the Monthly Security Bulletin to be issued in early September. Addressed in MSB issue number 153
59 | MUB | 42. Since security information is not to be included in the first phase of NOMIS there remains a need for a national database for security information. Establishments should have the 4X4 system converted to the 5X5 system if that has not already been done and the systems should be networked across the prison estate Digby Griffith/George Houghton | COMPLETED |  | Uncertain | Uncertain |  | Accepted in principle. The funding implications of networking local security information systems are being assessed against the option of upgrading C-NOMIS to provide a networked system. Security Group also are looking to see if C-NOMIS could be used for this. EDS have agreed that those establishments that do not currently have 5x5 will be provided with it as part of Quantum Refresh, all bar 4 establishments in the public sector have now been upgraded. Security Group are taking forward action to address this in the private prisons. Networking not possible at present.
60 | MUB | 43. Where prisoners have served a sentence before the security department should always obtain their security files from the establishment from which they were discharged. Accepted. Digby Griffith | PRODUCT 1.Better and quicker transfer of security information between establishments BENEFIT 1. Use of IT will enale implementation 2. Improved management of individual prisoners |  | None | None | Medium | High level decision taken to proceed with HMPS version of NOMIS | Amber | Amber | Until the detailed configuration of NOMIS is announced no further work can be taken forward at this time
61 | MUB | 44. Documents held in an establishment's administrative section should be vetted by staff from the Security Department, and each establishment should have a protocol for that work along the lines of the system for vetting security files. Requires further consideration. Digby Griffith/George Houghton | PRODUCT 1.Revision to National Security Framework (PSO 1000) and Local Security Strategies BENEFIT 1. Standardisation in procedures used across the estate 2. Improved management of individual prisoners | 2007-06-01 |  |  | Medium | High level decision taken to proceed with HMPS version of NOMIS | Amber | Amber | Until the detailed configuration of NOMIS is announced no further work can be taken forward at this time |  |  | Work currently halted pending wider consideration of future scope of C- NOMIS programme |  | Timings dependent upon C-NOMIS staff completing the required training. Indicative timings are to start process mapping in July and way forward agreed between SPU and C-NOMIS in December 2007
62 | MUB | PRISON INFORMATION STORE 47. The Prison Service should publish a model procedure dealing with how establishments should bring Prison Service Orders and other instructions, whether local or national which affect the management of prisoners to the attention of staff. The model procedure should be regarded as having been adopted by any establishment which does not produce one of its own. Gill Brigden | COMPLETED |  | None | None |  | Accepted: PSI 36/2006 issued 27 November 2006.
63 | MUB | 48. Governors should ensure that any relevant comments or recommendations in external reports about their establishments which have implications for the safety of prisoners be brought to the attention of the workforce. Gill Brigden | COMPLETED |  | None | None |  | Accepted. Such procedures are already in place at a number of establishments. PSI 32/2006 issued 27 November 2006.
64 | MUB | 50. The handbook giving guidance on how to complete the prisoner escort record should be revised to make it clear that this is not merely of use while a prisoner is in transit, but it is also intended to inform the prisoners management in the receiving establishment. It should give clear guidance to staff as to when a box should be ticked. Staff who are tasked with completing the form should be instructed on how to complete it by senior officers in their department. They should each be provided with a copy of the handbook, and they should be reminded of the need to spell out the reasons for a particular box being ticked. Digby Griffith/George Houghton | PRODUCT 1. New and improved Prisoner Escort Record (PER) form BENEFIT 1. Standardisation in procedures used across the estate 2. Improved management of individual prisoners | 01/08/2007 March 2008 May 2008 June 2008 July 2008 | None | Training and printing of new forms | Medium | Arranging for printing of PER forms. | Green | Green | Start Pilot March 2008 1st review of pilots May 2008 Complete Pilots July 2008 Evaluation Report August 2008 National Rollout October 2008 |  | Continue detailed preparation for the Pilots | Decision on funding to allow pilots to proceed |  | Finalise HMPS arrangements including drafting a PSI introducing the new PER
65 | MUB | MENTAL HEALTH 75. The responses of those members of staff who have attended the mental health awareness training course should be analysed to determine whether the course can be improved. The number of frontline staff attending the course should be increased, resources and staff deployment permitting. Accepted. The number of front line staff attending the mental health training course will increase to a target delivery figure of 9,138 (20% of operational staff) by March 2007. The current two-day mental health awareness training is being reviewed, and an evaluation of the Mental Health Awareness self-directed workbook will take place in September 2006: both reviews will have learner involvement. Richard Bradshaw |  | 2007-12-01 |  |  |  | Reviews completed, report due December. Significant changes to training likely. Development of a minimum standard for MHA training for custodial staff is underway. This material will match to the competency framework under development within HMPS. | Amber | Amber
66 | MUB | PARALLEL WORLDS 79. The Prison Service and CRE should address the key areas for development identified by the Inspectorate in 'Parallel Worlds' in managing the action plan, Implementing Race Equality: A shared agenda for change. Accepted. Beverley Thompson |  | Various |  | Nil additional |  | Progress on the Race Equality Action Plan continues in line with stated timeframes. Progress is regularly reviewed by the Programme Board and with PSMB on a quarterly basis. Head of REAG meets with the Chief Inspector of Prisons, Anne Owers, on a regular basis, who has confirmed that she is content with the progress being made on the areas for developments highlighted in Parallel Worlds. | Green | Green
67 | MUB | 85. The Prison Service and the CRE should investigate the desirability and feasibility of race relations liaison officers being recruited from outside the Prison Service. Beverley Thompson | COMPLETED |  |  |  |  | Accepted. The Prison Service fully supports the principle of recruiting Race Relations Liaison Officers from outside the Prison Service as well as from within the Service, and a number of establishments have already made such appointments. The revised PSO 2800 provides detailed guidance on the skills necessary for the enhanced role of the Race Equality Officer. It is left open for Governors to decide whether recruitment is also extended externally. However a number of establishments have already opted for external recruitment. It is not envisaged that this will become policy. This remains a local matter for Governors and is reflected in the new PSO 2800.
68 |  | Communications Develop and manage he REAG Communiction Strategy, that aims to promote race equality isssues Service-wide to establishments, headquarters groups, Prison Service management boards, OGDs and external stakeholders. Beverley Thompson | PRODUCT 1. Produce a Communications Strategy and communications plan 2. Arrange REAG conference | July 2007 September 2007 |  |  |  | 1. Draft Strategy produced May 2007. Further work on identifying the Group's key stakeholders and considering how best to communicate with them will be undertaken in November 2007. 2. REAG Conference "Uncovering Hidden Racism: The Next Challenge" was successfully held, and well received, on 27th September at the Emirates Stadium, London. | Green | Green